## Sheet1
SDLC GANTT CHART
Software Development Life Cycle (SDLC)
February
TASK | START | END | Duration | Status | 2025-01-26 | 2025-01-27 | 2025-01-28 | 2025-01-29 | 2025-01-30 | 2025-01-31 | 2025-02-01 | 2025-02-02 | 2025-02-03 | 2025-02-04 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-08 | 2025-02-09 | 2025-02-10 | 2025-02-11 | 2025-02-12 | 2025-02-13 | 2025-02-14 | 2025-02-15 | 2025-02-16 | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28
Assignment | 2025-01-26 | 2025-01-29 | 3 | Completed
Making of Assignment | 2025-01-30 | 2025-02-04 | 5 | Ongoing
Identifying a Potential Client and Orientation | 2025-01-30 | 2025-02-04 | 5
Conducted an Interview, and discussed the System with the Client and the Client signed the Consent | 2025-02-05 | 2025-02-06 | 1
Project Progress | 2025-02-07 | 2025-02-10 | 3
Details Requirements Meeting | 2025-02-11 | 2025-02-11 | 0
Conducted an Interview, and discussed the System with the new Client and the Client signed the Consent | 2025-02-12 | 2025-02-12 | 0
System Analysis & Requirement Approval | 2025-02-13 | 2025-02-19 | 6
System Design Preparation | 2025-02-20

## Sheet2
SDLC GANTT CHART
Software Development Life Cycle (SDLC)
START DATE:
END DATE:
TASK | START | END | DURATION
Assignment | 2025-01-26 | 2025-01-29 | 3
Making of Assignment | 2025-01-30 | 2025-02-04 | 5
Identifying a Potential Client and Orientation | 2025-01-30 | 2025-02-04 | 5
Conducted an Interview, and discussed the System with the Client and the Client signed the Consent | 2025-02-05 | 2025-02-06 | 1
Project Progress | 2025-02-07 | 2025-02-10 | 3
Details Requirements Meeting | 2025-02-11 | 2025-02-11 | 0
Conducted an Interview, and discussed the System with the new Client and the Client signed the Consent | 2025-02-12 | 2025-02-12 | 0
System Analysis & Requirement Approval | 2025-02-13 | 2025-02-19 | 6
System Design Preparation | 2025-02-20